Training Details & Logistics

FlexLine Business Credit

Learning Objectives:

- Upon completion, CX agents should be able to:

  - Reduce participant confusion by comparing and contrasting the characteristics and limitations of revolving lines of credit with other loan types

  - Define the fee structure within the FlexLine Business Credit

  - Recall and describe key characteristics and eligibility requirements of the FlexLine Business Credit

  - Cite the major Compliance violations surrounding FlexLine Business Credit participant discussions

  - Provide accurate responses to participant questions about the FlexLine Business Credit via role-play or scenario-based learning

Audience

- CX New Hires | Tenured agents

Timeline & Constraints

- Timeline:

  - 3 weeks | Go-Live

  - 2.5 weeks | LMS/Production Testing | Train-the-Trainer (T3)

  - 2 weeks | Training asset(s) final approval

  - 1.5 weeks | Submit training asset(s) for review & approval

  - 1 week | Training asset Alpha draft completion

- Constraints:

  - 20-minute max duration

  - Unknown immediate pre & post time slot content blocks

  - Singular independent training asset requirement

  - Polar opposite dual audience base

Success Evaluation Metrics

- (Level 1) | Learner Satisfaction Survey (course-level)

    - Is the information relevant? Engaging? Favorable?

- (Level 2) | Knowledge Checks & Scenario-based Role-play

- (Level 3) | Post-training job aid hit rates / Call reviews / Agent observations / Manager check-ins

- (Level 4) | 30/60/90-day post-training FlexLine Business Credit analytics

    - Trending decline? Trending rise?

      - Overall major Compliance violations

      - CSAT scores & targeted keyword

Deliverables

- Assets

  - eLearning Module

    - Branching structure

      - Course pulls learner data from LMS & automatically routes the leaner down the appropriate path.

      - Ability to select role title as manual contingency.

    - Reporting & Analytics

      - Non-graded Knowledge Check questions

      - Complete/Incomplete via completion trigger on final slide

      - Typical LMS SCORM package

      - Course survey via xAPI or another type of form to capture immediate learner feedback

  - Explainer Video

    - Animated story illustrating participant concerns and confusion with proper handling regarding the FlexLine Business Credit

    - Also to be included within the eLearning module

- Resources/Job Aids

  - FlexLine Business Credit speed sheet (new)

  - Loan Basics (assumed resource)

  - Loan Types (assumed resource)

  - Compliance QA Guidelines (assumed resource)